## Timeline of Tasks
The Singapore Dysphagia Diet Standardisation Committee is pleased to provide implementation tasks and timeframes needed for implementating the IDDSI framework in your institution. This document has been adapted from the International Dysphagia Diet Standardisation Initiative (IDDSI) implementation guide.
Please find below a 18 month calendar of events.
The key tasks include :
1. Form EatSafe SG implementation teams
2. Become familiar with IDDSI
3. Landscape scan and planning
4. EatSafe SG education and training
5. Diet and fluid preparation
6. System / process changes
Some of the tasks may run concurrently so it is important to look down the whole list. The Implementation guide is a suggestion! Please feel free to customize the tasks and timeframes to suit your own institutional needs.
Visit: https://www.moh.gov.sg/hpp/allied-health-professionals/eatsafe-sg
Glossary
ST: Speech Therapist
DIT: Dietitian
IDDSI: International Dysphagia Diet Standardisation Initiative
Overall Target Go-Live Date | [Institution to fill in date]
Progress to Go-Live | 2.222%
| Suggested Task Owner: | For Institution to Fill |  |  |  |  | MONTHS TO GO-LIVE
|  | Assigned Task Owner | Projected Start Date | Projected End Date | Progress Status | Comments / notes | 18 months to go | 17 months to go | 16 months to go | 15 months to go | 14 months to go | 13 months to go | 12 months to go | 11 months to go | 10 months to go | 9 months to go | 8 months to go | 7 months to go | 6 months to go | 5 months to go | 4 months to go | 3 months to go | 2 months to go | 1 months to go | Launch!
1. Form EatSafe SG Implementation Teams |  |  |  |  | 33.33%
Form a EatSafe SG Implementation team. Consider including your Food Service/Catering team, clinical and health care professional staff and all others affected by IDDSI implementation. Sample team could be made up of STs, Food Services / Kitchen staff, Dietitian and Nursing of your institution. | ST / DIT / Nurse manager |  | 2022-06-01 | 2022-12-01 | Done
Identify a Point-of-Contact (POC) from the Institutional Champions' team for: - Liaison with Singapore Dysphagia Diet Standardisation Committee (SDDSC) for updates - It is recommended that the POC is also one of the institutional champions. | Implementation team |  |  |  | In Progress
Meet with leadership / management to obtain approval to proceed with the implementation of the IDDSI framework within institution | Implementation team |  |  |  | Not Started Yet
Establish a regular platform with senior management to update and obtain approval for system level changes in a timely manner (E.g. IT system, menu changes). | Implementation team |  |  |  | Not Applicable
2. Become Familiar with IDDSI |  |  |  |  | 0%
Become familiar with the IDDSI website www.iddsi.org, particularly the Singapore page. You can also access MOH EatSafe SG website https://www.moh.gov.sg/hpp/allied-health-professionals/eatsafe-sg for latest information of IDDSI implementation in Singapore. | Implementation team |  |  |  | Team to Review Timeline
Refer to key IDDSI resources and those uploaded to the Singapore page (E.g. Testing methods, FAQs, Resources, IDDSI Application) | Implementation team |  |  |  | Team to Review Timeline
Decide on 'GO LIVE' date for full scale IDDSI implementation within your institution | Implementation team |  |  |  | Team to Review Timeline
Review the activities listed in this implementation guide (Sections 3-6). Confirm task owners and timeline according to the needs of your institution. | Implementation team |  |  |  | Team to Review Timeline
3. Landscape Scan and Planning |  |  |  |  | 0%
Using IDDSI fluid testing methods, map current fluid consistencies to the IDDSI framework. | ST / DIT |  |  |  | Team to Review Timeline
Identify the current number of diet texture levels served in institution and its descriptors | ST / DIT |  |  |  | Team to Review Timeline
Map your institution's current textures to IDDSI diet levels. Identify gaps with reference to the new standards (E.g. missing diet levels). Refer to the following documents: - 'IDDSI Framework and Detailed Level Definitions' - 'IDDSI Testing Method' | ST / DIT |  |  |  | Team to Review Timeline
Share results of baseline study on current fluid and diet texture levels available within the EatSafe SG implementation team | ST / DIT |  |  |  | Team to Review Timeline
Schedule regular EatSafe SG Implementation team meetings | Implementation team |  |  |  | Team to Review Timeline
Identify possible challenge areas and develop contingency plans (E.g. Kitchen is unable to prepare extra diet levels, limitations with IT system) | Implementation team |  |  |  | Team to Review Timeline
Decide on the duration of transition period before the 'GO LIVE' date (E.g. 3 months, 6 months) | Implementation team |  |  |  | Team to Review Timeline
To plan for the use of transitional labels (dual labeling) across systems / platforms (E.g. clinical documentation, education handouts, meal slips, menu systems) | Implementation team |  |  |  | Team to Review Timeline
Draft Policy & Procedures for the use of IDDSI framework in your institution and submit it to HOD / higher management for approval (where applicable) | Implementation team |  |  |  | Team to Review Timeline
Decide on indicators to measure success of implementation post 'GO LIVE' date (E.g. order entry errors, diet audit outcomes) | Implementation team |  |  |  | Team to Review Timeline
4. IDDSI Education and Training |  |  |  |  | 0%
Identify at least 3 Institutional Champions within your institutions. Consider having Insitutional Champions across various professions. Submit the details of the Institutional Champions via EatSafe SG Connect FormSG. | Implementation team |  |  |  | Team to Review Timeline
Come up with a timeline and training plan to send all staff for standardised national training. - Prioritise Institutional Champions and key staff to attend training first. Include new staff in plans. | Implementation team |  |  |  | Team to Review Timeline
Implementation team and Institutional Champions to complete standardised e-learning modules. Institutional Champions to attend compulsory Basic and Advanced hands-on workshops. | Implementation team and champions |  |  |  | Team to Review Timeline
All targetted Healthcare professionals (HCPs) who require training are to complete e-learning modules. Institutional Champions can also conduct Basic hands-on training workshop to their staff as required by institution. | All targetted HCPs (e.g. Doctors, nurses, care staff, dietitians, food service staff, speech therapists), institutional champions |  |  |  | Team to Review Timeline
Identify resources available on the MOH EatSafe SG website that are useful for your institution (E.g. Diet levels, audit tools, list of FAQs). Check the MOH EatSafe SG website periodically for updates related to EatSafe SG implementation. | Implementation team |  |  |  | Team to Review Timeline
Adapt current handouts and resources to include IDDSI terms. Determine the need for translation of documents other than the languages available on the IDDSI website. | Implementation team |  |  |  | Team to Review Timeline
Put up information posters at appropriate places | Implementation team |  |  |  | Team to Review Timeline | [12 empty] | Coincide with transition period (see row 41)
Introduce new patient education materials / handouts | Implementation team |  |  |  | Team to Review Timeline | [12 empty] | Coincide with transition period (see row 41)
Arrange for training for use of updated IT systems where needed. | Implementation team |  |  |  | Team to Review Timeline
Regularly update staff on the changes: - IDDSI implementation timelines - Training plan - Changes in menu and diet levels available - Patient education material - IT systems e.g. documentation, ordering system. | Implementation team |  |  |  | Team to Review Timeline
5. Diet and Fluid Preparation |  |  |  |  | 0%
Communicate EatSafe SG implementation framework and plan to food service staff. Where outsourced catering is involved, institutions may need to discuss contract specifications and review contracts as necessary | Implementation team/Food Services |  |  |  | Team to Review Timeline
Determine approach and commence review of the current menu and recipes in relation to IDDSI framework | Implementation team/Food Services |  |  |  | Team to Review Timeline
To identify and procure equipment to modify diet into the required specifications (E.g. blender, food processor) | Food Services |  |  |  | Team to Review Timeline
Review the current menu using IDDSI guidelines. Develop recipes required for modified diet textures, to meet national standards (to consider collaborating with Speech Therapists on the appropriate food items that can be used for the various diet textures). Refer to the EatSafe SG Resource List as needed. | Food Services / ST / DIT |  |  |  | Team to Review Timeline
Food Services and STs to collaborate and decide on what fluid levels are allowed for the various meals served (E.g. soup (IDDSI Level 0, thin fluids) cannot be served with diet (IDDSI Level 4,pureed)) | Food Services / ST / DIT |  |  |  | Team to Review Timeline
Food Services and STs to collaborate and ensure that all the components in a meal (E.g. main meal, soup, fruits, desserts) adhere to IDDSI guidelines. | Implementation team |  |  |  | Team to Review Timeline
To modify purchase of raw food materials needed for food preparation, in order to meet IDDSI guidelines. To continue as per current practice if no modification is required. | Food Services |  |  |  | Team to Review Timeline
Audit new recipes using IDDSI testing methods to ensure guidelines are met | Food Services / ST / DIT |  |  |  | Team to Review Timeline
Consider carrying out a pilot test in a specified ward as part of the recipe creation process, diet order entry, production, assembly, and meal delivery. Implementation team to evaluate and review processes after pilot test is completed. | Implementation team |  |  |  | Team to Review Timeline
Develop plans and timeline for full scale diet order entry, production, assembly and delivery systems | Implementation team |  |  |  | Team to Review Timeline
Develop and trial monitoring tools for production, assembly and delivery systems | Implementation team |  |  |  | Team to Review Timeline
Decide on the type of audits to be conducted in institution (E.g. preparation of fluids, meal audits) | Implementation team |  |  |  | Team to Review Timeline
Decide on regularity of these audits (E.g. once off, 6 monthly) and who would conduct these audits. | Implementation team |  |  |  | Team to Review Timeline
6. System / Process Changes |  |  |  |  | 0%
Identify IT systems that contains fluid and diet labels that need to be updated (e.g. electronic menu ordering systems, order forms, electronic medical records) | Implementation team |  |  |  | Team to Review Timeline
Meet with Food Services and Catering team to review diet order / entry system | Food Services / Implementation team / IT |  |  |  | Team to Review Timeline
Develop plans and timeline for necessary modifications of diet order / entry system | Implementation team / IT |  |  |  | Team to Review Timeline
Develop and effect necessary modification to IT systems for IDDSI implementation (e.g. menu systems, EMR) | Implementation team / IT |  |  |  | Team to Review Timeline
Introduce and monitor use of revised IT systems (E.g. clinical documentation, user feedback on ordering system) | Implementation team |  |  |  | Team to Review Timeline | [12 empty] | Coincide with transition period (see row 41)

## Progress At One Glance (hidden)
TASKS |  | Progress Status
1. Form EatSafe SG Implementation Teams |  | 33.33%
| Form a EatSafe SG Implementation team. Consider including your Food Service/Catering team, clinical and health care professional staff and all others affected by IDDSI implementation. Sample team could be made up of STs, Food Services / Kitchen staff, Dietitian and Nursing of your institution. | Done
| Identify a Point-of-Contact (POC) from the Institutional Champions' team for: - Liaison with Singapore Dysphagia Diet Standardisation Committee (SDDSC) for updates - It is recommended that the POC is also one of the institutional champions. | In Progress
| Meet with leadership / management to obtain approval to proceed with the implementation of the IDDSI framework within institution | Not Started Yet
| Establish a regular platform with senior management to update and obtain approval for system level changes in a timely manner (E.g. IT system, menu changes). | Not Applicable
2. Become Familiar with IDDSI |  | 0%
| Become familiar with the IDDSI website www.iddsi.org, particularly the Singapore page. You can also access MOH EatSafe SG website https://www.moh.gov.sg/hpp/allied-health-professionals/eatsafe-sg for latest information of IDDSI implementation in Singapore. | Team to Review Timeline
| Refer to key IDDSI resources and those uploaded to the Singapore page (E.g. Testing methods, FAQs, Resources, IDDSI Application) | Team to Review Timeline
| Decide on 'GO LIVE' date for full scale IDDSI implementation within your institution | Team to Review Timeline
| Review the activities listed in this implementation guide (Sections 3-6). Confirm task owners and timeline according to the needs of your institution. | Team to Review Timeline
3. Landscape Scan and Planning
Using IDDSI fluid testing methods, map current fluid consistencies to the IDDSI framework.
Identify the current number of diet texture levels served in institution and its descriptors
Map your institution's current textures to IDDSI diet levels. Identify gaps with reference to the new standards (E.g. missing diet levels). Refer to the following documents: - 'IDDSI Framework and Detailed Level Definitions' - 'IDDSI Testing Method'
Share results of baseline study on current fluid and diet texture levels available within the EatSafe SG implementation team
Schedule regular EatSafe SG Implementation team meetings
Identify possible challenge areas and develop contingency plans (E.g. Kitchen is unable to prepare extra diet levels, limitations with IT system)
Decide on the duration of transition period before the 'GO LIVE' date (E.g. 3 months, 6 months)
To plan for the use of transitional labels (dual labeling) across systems / platforms (E.g. clinical documentation, education handouts, meal slips, menu systems)
Draft Policy & Procedures for the use of IDDSI framework in your institution and submit it to HOD / higher management for approval (where applicable)
Decide on indicators to measure success of implementation post 'GO LIVE' date (E.g. order entry errors, diet audit outcomes)
4. IDDSI Education and Training
Identify at least 3 Institutional Champions within your institutions. Consider having Insitutional Champions across various professions. Submit the details of the Institutional Champions via EatSafe SG Connect FormSG.
Come up with a timeline and training plan to send all staff for standardised national training. - Prioritise Institutional Champions and key staff to attend training first. Include new staff in plans.
Implementation team and Institutional Champions to complete standardised e-learning modules. Institutional Champions to attend compulsory Basic and Advanced hands-on workshops.
All targetted Healthcare professionals (HCPs) who require training are to complete e-learning modules. Institutional Champions can also conduct Basic hands-on training workshop to their staff as required by institution.
Identify resources available on the MOH EatSafe SG website that are useful for your institution (E.g. Diet levels, audit tools, list of FAQs). Check the MOH EatSafe SG website periodically for updates related to EatSafe SG implementation.
Adapt current handouts and resources to include IDDSI terms. Determine the need for translation of documents other than the languages available on the IDDSI website.
Put up information posters at appropriate places
Introduce new patient education materials / handouts
Arrange for training for use of updated IT systems where needed.
Regularly update staff on the changes: - IDDSI implementation timelines - Training plan - Changes in menu and diet levels available - Patient education material - IT systems e.g. documentation, ordering system.
5. Diet and Fluid Preparation
Communicate EatSafe SG implementation framework and plan to food service staff. Where outsourced catering is involved, institutions may need to discuss contract specifications and review contracts as necessary
Determine approach and commence review of the current menu and recipes in relation to IDDSI framework
To identify and procure equipment to modify diet into the required specifications (E.g. blender, food processor)
Review the current menu using IDDSI guidelines. Develop recipes required for modified diet textures, to meet national standards (to consider collaborating with Speech Therapists on the appropriate food items that can be used for the various diet textures). Refer to the EatSafe SG Resource List as needed.
Food Services and STs to collaborate and decide on what fluid levels are allowed for the various meals served (E.g. soup (IDDSI Level 0, thin fluids) cannot be served with diet (IDDSI Level 4,pureed))
Food Services and STs to collaborate and ensure that all the components in a meal (E.g. main meal, soup, fruits, desserts) adhere to IDDSI guidelines.
To modify purchase of raw food materials needed for food preparation, in order to meet IDDSI guidelines. To continue as per current practice if no modification is required.
Audit new recipes using IDDSI testing methods to ensure guidelines are met
Consider carrying out a pilot test in a specified ward as part of the recipe creation process, diet order entry, production, assembly, and meal delivery. Implementation team to evaluate and review processes after pilot test is completed.
Develop plans and timeline for full scale diet order entry, production, assembly and delivery systems
Develop and trial monitoring tools for production, assembly and delivery systems
Decide on the type of audits to be conducted in institution (E.g. preparation of fluids, meal audits)
Decide on regularity of these audits (E.g. once off, 6 monthly) and who would conduct these audits.
6. System / Process Changes
Identify IT systems that contains fluid and diet labels that need to be updated (e.g. electronic menu ordering systems, order forms, electronic medical records)
Meet with Food Services and Catering team to review diet order / entry system
Develop plans and timeline for necessary modifications of diet order / entry system
Develop and effect necessary modification to IT systems for IDDSI implementation (e.g. menu systems, EMR)
Introduce and monitor use of revised IT systems (E.g. clinical documentation, user feedback on ordering system)

## Dropdown (To hide later) (hidden)
Progress status
Done
In Progress
Not Started Yet
Not Applicable
Team to Review Timeline